## Sheet1
T | F | M | T | W | T | F | M | T | W | T
Design overarching architecture
Initial Planning
| Writing libraries (some HAL some API) |  |  |  |  | minigame
|  | MVP |  |  |  | Music infrastructure
|  | Player |  |  |  | More levels and enemies
|  | Collisions |  |  |  |  | Design music
|  |  | Shooting |  |  |  |  | Write report
Menu
|  |  |  | Level infrastructure |  | Extra features (if time)
Enemies
Points and life
Hackertyper
Signals (buzzer/led)
Design first two levels
!!report during development |  |  |  |  | Powerup
Simon
Mads
Gustav |  |  |  | EXAM!
AT DTU?? | yes | yes |  | yes | yes |  | yes |  | yes | yes