## Sheet1
| Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday
| Design overarching architecture |  | Player | Shooting |  | Hackertyper | minigame |  | Write report
| Initial Planning |  | Collisions | Menu | Level infrastructure | Signals (buzzer/led) | Music infrastructure | Design music
|  | Writing libraries (some HAL some API) |  |  | Enemies | Design first two levels | More levels and enemies
|  |  | MVP |  | Points and life | Powerup | Extra features (if time)
At DTU? | yes | yes | yes | no | yes | yes | no | yes | no | yes | yes
Labels: | Simon
| Mads |  |  |  | Exam | Obligatory done |  | Feature freeze |  |  | Report deadline
Gustav
Everyone